## Sheet1
Week | Goals | Actions | Deliverables
2013-11-18 | Choosing game concept, choose tools, further organisation | W: work on story/setting, C: talk with KPMG about concepts, P: Try out/find right tools, V: determine visual type | Game design document |  |  |  | W | Writer
2013-11-25 | Sprint 1, Start working out minigame concepts | W: work out concept first mini-game. P: first sprint, V: prepare visuals for sprint 2 |  |  |  |  | C | Communications
2013-12-02 | Sprint 2, start on presentation, finish minigame concept | C: make slides, W: finish minigame concept, P: sprint 2, MP: Organise group testing, V: Start on visuals first minigame | Game prototype 1 |  |  |  | P | Programmer
2013-12-09 | Sprint 3, start conceptwork second minigame | C: finish presentation, W: Start concept second Mini-game, P: sprint 3, MP: Slide technical side | Mid-term presentation |  |  |  | L | Producer
2013-12-16 | Sprint 4, Finish concept second minigame | W: finishes concept, P: sprint 4, MP: plans second team testing, V: Start on visuals second mini-game | Prototype 2 |  |  |  | V | Visuals
2013-12-23 | Sprint 5 | W+C: Final documentation, P: sprint 5 | Christmas |  |  |  | MP | Master programmer
2013-12-30 | Sprint 5 | W+C: Final documentation, P: sprint 5 | Christmas
2014-01-06 | Sprint 6 | W+C: Final documentation, P: sprint 6, MP: plan Beta-testing
2014-01-13 | Sprint 7 | W+C: Finish documentation, P: sprint 7, MP: finish techical report | Final prototype plus documentation
2014-01-20 | finish + practice final presentation | All: presentation | Final presentation
|  |  |  | Sprint 1 | 1 week | Set up programming environment and application design
|  |  |  | Sprint 2 | 1 week | work out the game environment, without minigames
|  |  |  | Sprint 3 | 1 week | First implementation minigame
|  |  |  | Sprint 4 | 1 week | implement Reward system
|  |  |  | sprint 5 | 2 weeks | Finish implementing minigame and integrate it with reward system
|  |  |  | sprint 6 | 1 week | Implement second minigame
|  |  |  | Sprint 7 | 1 week | reserve/finish sprint